# REQUEST FOR PROPOSAL # 260000001743

Michigan Department of Transportation

Detroit Transportation Service Center

HMA/Concrete Pavement Repair on M-1 & M-3, City of Detroit, Wayne County

Solicitation Manager Name: Ruth Thole

Direct Phone: 517-335-4972

Email: TholeR@michigan.gov

This is a Request for Proposal (RFP) for services to perform pavement repair work on Woodward Ave/M-1 between Davison/M-8 and McNichols; and on Gratiot Ave/M-3 between St. Aubin and Mack.  The contract will require HMA and concrete work; including milling, removal of existing concrete overlay, concrete hand patching, curb and gutter, drainage structure adjustments and cleaning, pavement marking, providing traffic control, and other defined work.

RFP Timeline

| Event | Time | Date |
| --- | --- | --- |
| RFP issue date | N/A | April 14, 2026 |
| Deadline for bidders to submit questions about this RFP | 3:00 p.m. Eastern | April 21, 2026 |
| Anticipated date the State will post answers to bidder questions on www.michigan.gov/SIGMAVSS | 5:00 p.m. Eastern | April 22, 2026 |
| Proposal deadline* | 3:00 p.m. Eastern | April 28, 20226 |
| Anticipated contract begin date | N/A | May 14, 2026 |
| Work completion deadline | N/A | September 30, 2026 |

*A bidder’s proposal received at 3:00:01 p.m. Eastern is late and subject to disqualification.

This RFP is subject to change. Check www.michigan.gov/SIGMAVSS for current information.

# proposal instructions

- PROPOSAL PREPARATION. The State recommends reading all RFP materials prior to preparing a proposal, particularly these Proposal Instructions and the Vendor Questions Worksheet. Bidders must follow these Proposal Instructions and provide a complete response to the items indicated in the table below. References and links to websites or external sources may not be used in lieu of providing the information requested in the RFP within the proposal. Include the bidder’s company name in the header of all documents submitted with your proposal. Note that all documents and information submitted as part of a proposal will become public record immediately upon receipt by the State.  Proposals received by the State may be posted on the State’s publicly available website after bidders are notified of the award recommendation.

RFP Structure and Documentation

| Document | Description | Bidder Response Instructions |
| --- | --- | --- |
| Cover Page | Provides RFP title and number, important dates, and contact information for Solicitation Manager | Informational |
| Proposal Instructions | Provides RFP instructions to bidders | Informational |
| Vendor Questions Worksheet | Questions to bidders on background and experience | Bidder to complete and submit by proposal deadline |
| Schedule A – Statement of Work | Statement of work | Bidder to complete and submit by proposal deadline |
| Contract Terms | Provides legal terms for a contract awarded through this RFP | Deemed accepted by bidder unless bidder submits proposed changes to the Contract Terms in track changes (i.e., visible edits) with an explanation of the bidder’s need for each proposed change. |
| Schedule B – Pricing | Pricing for goods and services sought by the State through this RFP | Bidder to complete and submit by proposal deadline |
| Exhibit 1A – Woodward Ave M-1 Plans | Plans for work on Woodward Ave/M-1 | Informational |
| Exhibit 1B – Gratiot Ave M-3 Maps & Plans | Maps and Plans for work on Gratiot Ave/M-3 | Informational |
| Exhibit 2 – Brick Paver Transport & Storage | Maps to storage locations for salvaged brick pavers | Informational |
| Exhibit 3 – HMA Mill and Fill Sample | Requirements for mill and fill through intersections and driveways | Informational |
| Attachment A – Prevailing Wage Information and Rates for Wayne County | Current prevailing wages | Contractor must post the scale of wages to be paid in a prominent and easily accessible place at the site of the work. |

- CONTACT INFORMATION FOR THE STATE. The sole point of contact for the State concerning this RFP is:

Ruth Thole, Solicitation Manager

517-335-4972

TholeR@michigan.gov

Contacting any other State personnel, agent, consultant, or representative about this RFP may result in bidder disqualification.

- MODIFICATIONS. The State may modify this RFP at any time. Modifications will be posted on www.michigan.gov/SIGMAVSS. This is the only method by which the RFP may be modified.

- QUESTIONS. Bidder questions about this RFP must be emailed to the Solicitation Manager at TholeR@michigan.gov no later than 3:00 pm Eastern Time on April 21, 2026. In the interest of transparency, only written questions are accepted. Answers to questions will be posted on www.michigan.gov/SIGMAVSS.

- DELIVERY OF PROPOSAL. The bidder must submit its proposal, all attachments, and any modifications or withdrawals electronically through www.michigan.gov/SIGMAVSS. The price proposal should be saved separately from all other proposal documents. The bidder should submit all documents in a modifiable (native) format (examples include but are not limited to Microsoft Word or Excel and Google Docs or Sheets). In addition to submitting documents in a modifiable format, the bidder may also submit copies of documents in PDF. Attachment file size is limited to 30 MB per document. Bidder’s failure to submit a proposal as required may result in disqualification. The proposal and attachments must be fully uploaded and submitted prior to the proposal deadline. Do not wait until the last minute to submit a proposal, as the SIGMA VSS system requires the creation of an account and entry of certain information, in addition to uploading and submitting the materials. The SIGMA VSS system will not allow a proposal to be submitted after the proposal deadline identified in the solicitation Closing On/Closing Date fields (Summary view/Detail view), even if a portion of the proposal has been uploaded.

Questions on how to submit information or how to navigate in the SIGMA VSS system can be answered by calling (517) 284-0540 or (888) 734-9749. The Solicitation Manager will not provide assistance related to the submittal of the proposal and all attachments on the day of the proposal deadline. Responsibility for a complete submission lies with the bidder. Note that all documents and information submitted in any manner as part of a proposal will become public record immediately upon receipt by the State.  Proposals received may be posted by the State on the State’s publicly available website after bidders are notified of the award recommendation.

- MANDATORY MINIMUM REQUIREMENTS. To avoid disqualification, the bidder must meet the following mandatory requirements.  Only proposals meeting the mandatory minimum requirements will be considered for evaluation.

- Bidder must be currently listed as a MDOT Prequalified Contractor in the following category(s):

Cb (Hot Mix Asphalt/Bituminous Paving)

Ba – Concrete Pavement Patching

J – Concrete Curb, Curb & Gutter, Sidewalks

The list of Prequalified Contractors may be found at https://mdotjboss.state.mi.us/PSVR/PrequalifiedContractors.htm.

If the bidder is not prequalified in the required categories, they must indicate in its proposal a currently listed prequalified contractor(s) as the subcontractor(s).

- In accordance with Public Act 10 of 2023 (see MCL - Act 10 of 2023 - Michigan Legislature), the bidder and all subcontractors of the bidder must be registered with the Michigan Department of Labor and Economic Opportunity (LEO) to perform work on State of Michigan projects. A copy of the bidder’s and their listed subcontractors’ active State Project Registration Confirmation letter (provided by LEO) must be submitted with bidder’s solicitation response.

Registration for State Project Contractor may be completed on the LEO website, LEO - Prevailing Wage.

- EVALUATION PROCESS The State will evaluate each proposal on a PASS/FAIL basis based on the following criteria:

|  | Criteria | Pass/Fail |
| --- | --- | --- |
| 1. | Responses to Vendor Questions are complete and acceptable |  |
| 2. | Responses on Schedule A are complete and acceptable |  |
| 3. | Schedule B is complete |  |

The State may utilize all bidder information to determine fair market value for goods or services sought. If applicable, the State’s evaluation will include consideration of a bidder’s qualified disabled veterans/service-disabled veteran owned business(QDV/SDVOB) status under MCL 18.1261(8). Additional information on the SDVOB preference is available at: Michigan.gov/SDVOB.

The State may but is not required to conduct an on-site visit to tour and inspect the bidder’s facilities; require an oral presentation of the bidder's proposal; conduct interviews, research, reference checks, and background checks; and request additional price concessions at any point during the evaluation process.

- NOTICE OF DEFICIENCY. The State reserves the right to issue a Notice of Deficiency to bidders if the State determines after the proposal deadline that a portion of the RFP was deficient, unclear, or ambiguous. Failure to respond to a Notice of Deficiency timely may be cause for disqualification.

- CLARIFICATION REQUEST. The State reserves the right to issue a Clarification Request to a bidder to clarify its proposal if the State determines the proposal is not clear. Failure to respond to a Clarification Request timely may be cause for disqualification.

- RESERVATIONS. The State reserves the right to:

  - Disqualify a bidder for failure to follow these instructions.

  - Discontinue the RFP process at any time for any or no reason. The issuance of an RFP, your preparation and submission of a proposal, and the State’s subsequent receipt and evaluation of your proposal does not commit the State to award a contract to you or anyone, even if all the requirements in the RFP are met.

  - Consider late proposals if: (i) no other proposals are received; (ii) no complete proposals are received; (iii) the State received complete proposals, but the proposals did not meet mandatory minimum requirements or technical criteria; or (iv) the award process fails to result in an award.

  - Consider an otherwise disqualified proposal if no other proposals are received.

  - Disqualify a proposal based on: (i) information provided by the bidder in response to this RFP; (2) the bidder’s failure to complete registration on www.michigan.gov/SIGMAVSS ; or (3) if it is determined that a bidder purposely or willfully submitted false or misleading information in response to the RFP.

  - Consider prior performance with the State in making its award decision.

  - Consider overall economic impact to the State when evaluating proposal pricing and in the final award recommendation. This includes but is not limited to: considering principal place of performance, number of Michigan citizens employed or potentially employed, dollars paid to Michigan residents, Michigan capital investments, job creation, tax revenue implications, and economically disadvantaged businesses.

  - Consider total-cost-of-ownership factors (e.g., transition and training costs) when evaluating proposal pricing and in the final award recommendation.

  - Refuse to award a contract to any bidder that has failed to pay State taxes or has outstanding debt with the State.

  - Enter into negotiations with one or more bidders on price, terms, technical requirements, or other deliverables.

  - Evaluate the proposal outside the scope identified in the Evaluation Process section of this document if the State receives only one proposal.

- AWARD RECOMMENDATION. The contract will be awarded to the responsive and responsible bidder who receives a PASS for each criterion and has the lowest price.

The State will publish an Award Recommendation and Evaluation Synopsis, by posting a Notice of Intent to Award (NIA1) on www.michigan.gov/SIGMAVSS.

- DEBRIEF MEETING AND BID PROTEST. The State will post an Award Recommendation and Evaluation Synopsis which will provide instructions on how to request a debrief meeting.

If you wish to initiate a protest of the award, you must submit your written protest to Michael Meddaugh at MeddaughM@Michigan.gov no later than 3:00 p.m., three (3) business days after posting the Award Recommendation and Evaluation Synopsis on SIGMA VSS. The State reserves the right to adjust this timing and will publish any change.

Additional information about the protest process is available at DTMB - Programs and Policies (michigan.gov) under the “Bidder Protests” link.

- STATE ADMINISTRATIVE BOARD. Contracts equal to or greater than $500,000 require approval by the State Administrative Board. The State Administrative Board’s decision is final; however, its approval does not constitute a contract. The award process is not complete until the awarded contractor receives a contract fully executed by all parties.

- GENERAL CONDITIONS. The State will not be liable for any costs, expenses, or damages incurred by a bidder participating in this solicitation. The bidder agrees that its proposal will be considered an offer to do business with the State in accordance with its proposal, including the Contract Terms, and that its proposal will be irrevocable and binding for a period of 180 calendar days from date of submission. If a contract is awarded to the bidder, the State may, at its option, incorporate any part of the bidder’s proposal into a contract. This RFP is not an offer to enter into a contract. This RFP may not provide a complete statement of the State’s environment or contain all matters upon which agreement must be reached. The bidder understands that their proposal will become public record immediately upon receipt by the State. Other than verified trade secrets, proposals submitted via www.michigan.gov/SIGMAVSS are the State’s property.

- THE FREEDOM OF INFORMATION ACT. As a public record, all portions of the bidder’s proposal and resulting contract are subject to disclosure as required under Michigan’s Freedom of Information Act (FOIA), MCL 15.231, et seq.

  - NO ADVICE. The State will not advise a bidder as to the nature or content of documents entitled to protection from disclosure under FOIA or other laws, as to the interpretation of such laws, or as to the definition of trade secret or financial or proprietary information. Nothing contained in this provision will modify or amend requirements and obligations imposed on the State by FOIA or other applicable law.

  - The State has the final authority to determine whether the materials are exempt from disclosure under FOIA.  Bidder forever releases the State, its departments, subdivisions, officers, and employees from all claims, rights, actions, demands, damages, liabilities, expenses and fees, which arise out of or relate to the disclosure of all or a portion of bidder’s proposal submitted under this RFP. Bidder must defend, indemnify and hold the State, its departments, subdivisions, officers, and employees harmless, without limitation, from and against all actions, claims, losses, liabilities, damages, costs, attorney fees, and expenses (including those required to establish the right to indemnification), arising out of or relating to any FOIA request, including potential litigation and appeals, related to the portion of bidder’s proposal submitted under this RFP that bidder has identified as a trade secret, or financial or proprietary information. The State will notify bidder in writing if indemnification is sought. The State is entitled to: (i) regular updates on proceeding status; (ii) participate in the defense of the proceeding; (iii) employ its own counsel; and to (iv) retain control of the defense, or any portion thereof, if the State deems necessary. Bidder will not, without the State’s written consent (not to be unreasonably withheld), settle, compromise, or consent to the entry of any judgment in or otherwise seek to terminate any claim, action, or proceeding. If a State employee, official, or law is involved or challenged, the State may control the defense of that portion of the claim. Any litigation activity on behalf of the State, or any of its subdivisions under this Section, must be coordinated with the Department of Attorney General. An attorney designated to represent the State may not do so until approved by the Michigan Attorney General and appointed as a Special Assistant Attorney General.

# vendor questions worksheet

Provide a detailed response to each question. “You” and “company” refers to the bidder.  Information in this section such as legal name, doing business as, vendor customer code, business address, etc., MUST match your Vendor Profile in SIGMA VSS.

| Information Sought | Bidder Response |
| --- | --- |
| - Contact Information |  |
| Bidder’s sole contact person during the RFP process: |  |
| Name: |  |
| Title: |  |
| Address: |  |
| Phone Number: |  |
| Email: |  |
| Person authorized to receive and sign a resulting contract: |  |
| Name: |  |
| Title: |  |
| Phone Number: |  |
| Email: |  |
| Sole contact authorized to give and receive Notices (see Standard Contract Terms, Point 2.) |  |
| Name, email address, and phone number. Include address if different than legal business address |  |
| Contractor’s Contract Administrator (see Standard Contract Terms, Point 3.) |  |
| Name, email address, and phone number. Include address if different than legal business address |  |
| Contractor’s Program Manager (see Standard Contract Terms, Point 4.) |  |
| Name, email address, and phone number. Include address if different than legal business address |  |
| - Company Background Information |  |
| Legal business name. |  |
| Legal business address. |  |
| Business entity designation, e.g., sole proprietor, corporation, LLC, or LLP. |  |
| What state was the company formed in? |  |
| Phone number. |  |
| Legal business name and address of parent company, if any. |  |
| Has bidder ever been debarred, suspended, or disqualified from bidding or contracting with any entity, including the State of Michigan? If yes, provide the date, the entity, and details about the situation. |  |
| Has your company been a party to litigation against the State of Michigan? If the answer is yes, then state the date of initial filing, case name and court number, and jurisdiction. |  |
| Within the last 5 years, has your company or any of its related business entities defaulted on a contract or had a contract terminated for cause? If yes, provide the date, contracting entity, type of contract, and details about the termination or default. |  |
| Bidder affirms that any business types identified on its SIGMA VSS profile, including those eligible for Geographically Disadvantaged Business Enterprise (GDBE) and Michigan Supplier Community Program (MiSC), are valid. | Choose an item. |

- Qualified Disabled Veteran/Service-Disabled Veteran-Owned Business Program

Under MCL 18.1261, a “qualified disabled veteran” means a business entity that is 51% or more owned by 1 or more veterans with a service-connected disability. A “service-connected disability” means a disability incurred or aggravated in the line of duty in the active military, naval, or air service as described in 38 USC 101(16). To demonstrate qualification as a qualified disabled veteran, you must provide: A. Proof of service and conditions of discharge (DD214 or equivalent). B. Proof of service-connected disability (DD214 if the disability was documented at discharge or Veterans Administration Rating Decision Letter or equivalent if the disability was documented after discharge). C. Legal documents setting forth the ownership of the business entity. In lieu of the documentation identified above, the Contractor may provide proof of certification by the National Veterans Business Development Council.

| Does the bidder qualify as Disabled Veteran/Service-Disabled Veteran-Owned Business? | Choose an item. |
| --- | --- |
| If yes, enter the names of documents submitted with your proposal to demonstrate status as a qualified disabled veteran. |  |

| Information Sought | Bidder Response |
| --- | --- |
| - Standard Contract Terms |  |
| Bidder must affirm agreement with the attached Contract Terms. If not in agreement, bidder must submit proposed changes to the Contract Terms in track changes (i.e., visible edits) with an explanation of the bidder’s need for each proposed change. |  |
| - Michigan Voluntary Protection Program |  |
| Bidder must verify if their company is recognized in the Michigan Voluntary Protection Program (MVPP) | Choose an item. |
| - Labor, Antidiscrimination and Environmental Laws Compliance |  |
| Bidder must disclose any violations of state or federal labor, antidiscrimination and employment laws and regulations received within the past five years. |  |
| Bidder must disclose any violations of state or federal environmental laws and regulations received within the past five years. |  |
| - Other |  |
| Classification of Employees. I certify that the company has properly classified its employees in accordance with federal/state labor and employment laws. | Choose an item. |
| Abusive Labor Practices. The Contractor certifies that it will not furnish any Deliverable that was produced fully or partially by forced labor, forced or indentured child labor, or indentured servitude. | Choose an item. |
| Certification of Michigan Business- Public Act 431 of 1984, Sec. 268. I certify that the company has, pursuant to the provisions of Sec 268 of Public Act 431 of 1984, filed a Michigan Business Tax Corporate Income Tax Return. I certify that the company has, pursuant to the provisions of Sec 268 of Public Act 431 of 1984, filed a Michigan Income Tax return showing income generated in, or attributed to the State of Michigan. I certify that the company has, pursuant to the provisions of Sec 268 of Public Act 431 of 1984, withheld Michigan Income Tax from compensation paid to the company’s owners and remitted the tax to the Michigan Department of Treasury. | Choose an item. |
| Iran Linked Business- Public Act 517 of 2012. I certify that the Company is not an Iran-Linked business as defined by Public Act 517 of 2012. | Choose an item. |
| Clean Corporate Citizen. I certify that the Company is a Clean Corporate Citizen as defined by the Environmental Protection Act, 1994 PA 451. | Choose an item. |
| Convict Labor. The Contractor certifies that if using convict labor, it is complying with all applicable state and federal laws and policies. | Choose an item. |
| SOM Debt/Tax Payment. All SOM tax/debts. I certify that all applicable State of Michigan taxes are paid, and that no outstanding debt is owed to the State of Michigan. | Choose an item. |
| Authorization to Verify Information Provided by Vendor. I authorize the State to verify that all information provided in this registration, in bidding and contracting documents, and any attachments or supplement documents and processes are accurate. | Choose an item. |
| - Response to State Requests |  |
| Bidder agrees to respond, by established deadlines, to all requests from the State including but not limited to, clarification requests, notices of deficiency, and proposed changes to Contract Terms. | Choose an item. |

Contractor must enter company name here.

# Schedule A – statement of work

Request for Proposal (RFP) No. 260000001743

HMA/Concrete Pavement Repair on M-1 & M-3, City of Detroit, Wayne County

This schedule identifies the anticipated requirements of any Contract resulting from this RFP. The term “Contractor” in this document refers to a bidder responding to this RFP, as well as the Contractor who is awarded the contract. The term “bidder” is used to identify where specific responses to the RFP are required.

The Contractor must respond to each requirement or question and explain how it will fulfill each requirement. Attach any supplemental information and appropriately reference within your response.

IMPORTANT NOTE TO CONTRACTORS/BIDDERS: There are specific requirements for which acceptance must be simply acknowledged through a checkbox(es), and others that require further explanation. Click one checkbox and complete the entries as identified.

SCOPE

Michigan Department of Transportation (MDOT), Detroit Transportation Service Center is seeking a Prequalified Maintenance Contractor to perform the following repairs on streets located in the City of Detroit, Wayne County.

- Woodward Avenue (M-1) between Davison FWY (M-8) and McNichols Road.  Work includes full width (1.5” Depth) milling, 1.5” HMA overlay pavement repairs, removing brick pavers under the railroad and transporting the pavers for storage at different locations, adjusting base of areas where pavers were removed and resurfacing with 1.5” HMA, concrete hand patching, curb and gutter, structure adjustments and drainage cleaning, pavement marking, and providing traffic control.

- Gratiot Avenue (M-3) between St. Aubin Street and Mack Avenue. Work includes removing the existing concrete overlay from full 2 lanes and some patches from the other 2 lanes (3”-5” Depth) and underlying HMA scratch course; preparing the underlying concrete base; removing any neoprene seals; and overlay with HMA (2.5” max a course depth) concrete hand patching; curb and gutter; drainage structure adjustments and cleaning; pavement marking; and providing traffic control.

All Contract Activities must be in accordance with the Contract Provisions and referenced Documents.

- REQUIREMENTS

  - General Requirements

- The Contractor shall provide all labor, material, equipment, supervision, and any incidental services or items required to perform Contract Activities.

- Except where otherwise indicated within this Schedule A, all materials and workmanship shall be in accordance with the MDOT Standard Specifications for Construction, 2020 Edition [see MDOT 2020 Standard Specifications for Construction [WEB]-linked (michigan.gov)], and in accordance with the Special Provisions herein.

- The Contractor must not leave equipment and/or store equipment overnight on any trunkline, State right-of-way, or public recreational property during the performance of the Contract.  The Contractor must not operate or park equipment or store materials within a tree drip line.

- All local noise, dust, and work-hour ordinances shall apply to the Contract.

- MDOT will not be responsible for any cost associated with the disposal of any service provided in the Contract. MDOT will not be responsible for any citations, fines or tickets received, while performing Contract Activities.

- The Contractor must protect the safety and health of the public, state employees, State property and property of the local unit of government during the performance of the Contract.

- The Contractor shall conduct and supervise work as to ensure its completion in accordance with the terms of this contract and the approved progress schedule.

  - Specific Requirements

- See Exhibit 1A – Woodward Ave M-1 Plans and Exhibit 1B – Gratiot Ave M-3 Maps & Plans for approximate repair locations.

- See all Schedules, Exhibits, Attachments, and referenced documents for additional specific requirements for the project.

  - Miss Dig / Underground Utility Notification

- For the protection of underground utilities and in conformance with Public Act 174 of 2013, the Contractor must contact MISS DIG System, Inc. a minimum of three (3) business days prior to excavation.  MISS DIG must be contacted by phone at 811 or 800-482-7171 or via the web at Michigan Utility Notification Center - MISS DIG System (https://missdig811.org).

- The Contractor must complete form 5300 MDOT Underground Infrastructure Staking Request Form (see MDOT UNDERGROUND INFRASTRUCTURE STAKING REQUEST FORM) and submit the completed form and attachments to the applicable MDOT Metro Region addresses indicated on the form.  The form must be emailed at least five (5) business days prior to the anticipated start date of digging work.  The staking request form covers the following utilities which are not part of MISS DIG:

- MDOT electrical systems

- MDOT traffic counters

- MDOT signal loops

| ☐ | I have reviewed Section 1 requirements and agree with no exception. |
| --- | --- |
| ☐ | I have reviewed Section 1 requirements and have noted all exception(s) below. |
| List all exception(s): |  |

- DESCRIPTION OF WORK

All Pay Item quantities stated on Schedule B - Pricing and/or the work limits are subject to change.  The MDOT Program Manager will notify the Contractor about any change in the quantities or the limit of work (decrease and/or increase) which may result based on the MDOT budget, the Contractor’s bid price, or unforeseen pavement conditions.

  - HMA and Concrete Work

- Woodward Ave/M-1

- HMA repairs consist of full lane width milling of the surface at an average depth of 1.5” and placement of HMA.

- Brick paver removal, transport, and storage (see Exhibit 2) must be coordinated with the active project at the storage area.

- Brick paver removal area (average depth of 3”) will use wedging and/or leveling material to match the milled surface before the resurfacing with the 1.5” HMA.

- Any material under the brick pavers shall be removed to the existing concrete base then prepare the underlying concrete base.

- Concrete hand patching, curb and gutter, drainage structure adjustments and cleaning, pavement marking, and other defined work if needed as directed by the MDOT Program Manager.

- Gratiot Ave/M-3

- Remove the existing concrete overlay (3”-5” Depth) and underlying HMA scratch course. Prepare the underlying concrete base, remove any neoprene seals within the middle two lanes and some locations within the right and left lanes.

- Any HMA overlay and/or cold patch shall be removed to the concrete base then cleaned and prepared as mentioned in the above subsection 1).

- The HMA Overlay course depth is 2.5” maximum and shall use a leveling course and/or wedging, if needed, as directed by the MDOT Program Manager.

- Any full depth concrete patch shall be milled 1.5” minimum or as directed by the MDOT Program Manager.

- Concrete hand patching, curb and gutter, drainage structure adjustments and cleaning, pavement marking, and other defined work if needed as directed by the MDOT Program Manager.

- Milling and placement of HMA will be in accordance with Exhibit 3 – HMA Mill and Fill Sample or as directed by the MDOT Program Manager.

- The wedging and HMA hand patching, if needed, will be considered part of the HMA pay item.

- The HMA mix used for this project will be 4EML with PG 64-28 binder.

- A concrete mix and HMA pavement mix design must be pre-approved by the MDOT Program Manager.

- The existing composite pavement sections must have HMA repairs as marked by the MDOT Program Manager.

- All concrete work (concrete hand patching, curb and gutter, and/or sidewalk repairs) must be performed in accordance with Standard Plan R-44-F Concrete Pavement Repair (see R-44-F), Standard Plan R-28-K Curb Ramp and Detectable Warning Details (see R-28-K) , and Standard Plan R-30-G Concrete Curb and Concrete Curb & Gutter (see R-30-G).

- All joints and all saw cuts that were made on pavements, shoulders or gutters caused by overcutting must be cleaned and then sealed.

  - Pavt Rem (Item 2040050)

The Contractor must remove and dispose of the existing overlay pavement sections, including but not limited to concrete, brick pavers, and HMA patches without disturbing the base, as shown on Exhibits 1A and 1B plans.  Pavement materials must be removed to the concrete base and the limits shown on Exhibits 1A and 1B regardless of the existing material type or number of layers and thickness of individual layers in accordance with subsection 204.04 of the Standard Specifications for Construction.

Existing pavers must be removed at the locations specified by the MDOT Program Manager or designee using methods that will avoid damage to the pavers. Pavers not suitable for reuse must be disposed of according to section 204 of the Standard Specifications for Construction.

  - Pavement Repr, Rem (Item 6030080)

The Contractor must remove and dispose full depth of the existing pavement sections that needs to be replaced as directed by the MDOT Program Manager. The Pavt Repr, Rem is accordance with subsection 603.04 of the Standard Specifications for Construction.

  - Transporting Salvaged MDOT Materials

Any pavers removed during the pavement removal operation and approved for reuse by the MDOT Program Manager or designee must be stockpiled in a secure location.  The Contractor must upload, transport, and unload salvaged pavers to the storage area as shown on Exhibit 2 – Brick Paver Transport & Storage using methods that will not cause damage.  Handle, transport and store pavers to ensure the condition remains acceptable for reuse after completion of salvage work.

  - Drainage Structure Adjustments

Any drainage structures/catch basins that are marked for repair shall be constructed in accordance with Special Provision 20SP-403A-02 for Adjusting Drainage Structure (see 20SP-403A-02).

  - Drainage Structure and Lead Cleaning

- Drainage structure cleaning consists of cleaning existing catch basins and manholes in the area of the project where directed by the MDOT Engineer.  Drainage structure lead cleaning consists of cleaning sewer lines between catch basins and/or between catch basins and manholes.

- All cleaning work must be performed in accordance with Section 403.03. G. Cleaning Existing Drainage Structures and Leads of the Standard Specifications for Construction.

- Cleaning shall be by high velocity hydro-cleaning (jetting). Mechanical cleaning shall only be used when authorized by the MDOT Engineer. Contractor shall take precautions to protect the sewer lines from damage.

- No debris shall be accumulated on site except in totally enclosed containers approved by the MDOT Engineer. All material deposits shall be removed from site and disposed of at an approved location.

- The MDOT Engineer shall determine actual condition and necessity for cleaning prior to clean out. Cleaning shall restore a minimum 90% of the pipe's carrying capacity.

  - Erosion Control, Inlet Protection, Fabric Drop

- Furnish, install, and remove inlet protection in accordance with Special Provision for Erosion Control, Inlet Protection, Fabric Drop (see 20SP-208B-01).

- Protect storm drains and inlets from construction pollutants by placing inlet filters.  All storm drains marked by the MDOT Program Manager shall be protected with Inlet filter bags prior to beginning any saw cutting work.

- If filter bags cause pavement flooding issues during any rain event during the construction period, the Contractor shall remove any filter bags as directed by MDOT.  Filter bags must be removed within two (2) hours of MDOT notification.  Removal and replacement of filter bags will be at no additional cost to MDOT.

- Immediately after construction in a specific section is complete, remove temporary sediment control and dispose of construction pollutant; all used filter bags must be removed before moving to the next construction section.

  - Pavement Markings

- The Contractor must inventory existing pavement markings before pavement surface removal.  The Contractor must re-install pavement markings per inventory taken prior to pavement removal. Utilize the following Pavement Marking Standards [all Pavement Marking Standards may be found at MDOT - Transportation Standards and Special Details]:

- PAVE-900-G

- PAVE-901-A

- PAVE-905-E

- PAVE-906-C

- PAVE-907-A

- PAVE-930-D

- PAVE-935-E

- PAVE-940-D

- PAVE-945-D

- PAVE-946-A

- Use of temporary pavement markings is not allowed unless approved by MDOT.

- The Contractor must use Polyurea pavement marking.  Use of any other pavement marking material must have prior approval from the MDOT Program Manager.

  - Sweeping

Paved surfaces must be swept as often as necessary as directed by the MDOT Program Manager or designee and in accordance with Special Provision 20SP-107A-01 for Sweeping (see 20SP-107A-01).

| ☐ | I have reviewed Section 2 requirements and agree with no exception. |
| --- | --- |
| ☐ | I have reviewed Section 2 requirements and have noted all exception(s) below. |
| List all exception(s): |  |

- TRAFFIC CONTROL

  - Construction Influence Area (CIA)

- The CIA includes the right-of-way of the following roadways, within the approximate limits described below.

- On M-1 from approximately 1/4 mile south of M-8 to 1/4 mile north of McNichols.

- On NB M-3 from approximately 1/4 mile south of Saint Aubin St. to 1/4 mile north of Mack Ave.

- The CIA includes right-of-way of any designated detour route or alternate route, intersecting roads and ramps adjacent to the work zone for a distance of approximately 1/4 mile in advance of the work zone or as far as the construction or detour signing extends.

  - Requirements

- Traffic and traffic control must be maintained throughout the project in accordance with the following:

- Section 812 of the MDOT 2020 Standard Specifications for Construction

- Applicable MDOT Maintaining Traffic Typicals

- Current edition of the Michigan Manual of Uniform Traffic Control Devices (MMUTCD)

- Chapter 8 of the Work Zone Safety and Mobility Manual

- All Contract Activities must be conducted in a manner that will not create a hazard, nor hinder, restrict, or impede trunkline traffic. The Contractor must not operate equipment on the roadway or in a manner that requires unnecessary crossing of the roadway.

- The Contractor shall not park equipment within the right of way of any state trunkline in a manner not permitted by posted traffic control devices.

  - Traffic Control Plan

- Prior to starting work, the Contractor must submit a traffic control plan to the MDOT Program Manager for review/approval.

- Traffic closures must be requested by completing a Lane Closure Request (LCR) form [see MDOT LANE CLOSURE NOTIFICATION/REQUEST FORM (state.mi.us)].  The LCR must be submitted seven (7) days in advance of closure by sending to the MDOT Program Manager and planned lane closures must be submitted weekly to the MDOT Program Manager or designee. Daily closure updates must be called into SEMTOC at (313) 965-0777.  Updates must describe work zone boundaries for the day and any work that is postponed.

  - Traffic Restrictions

- Traffic must be maintained in accordance with regulations and notes contained herein. Changes or adjustments may be necessary to fit field conditions, subject to approval by or as determined by the MDOT Engineer.

- The minimum lane width for traveling traffic will always be 11 feet.

- Maintain a minimum of one lane of travel in each direction at all times M-1 and M-3 (and all intersecting road and ramps, except where detoured).

- Maintain all cross traffic, driveways, intersections, and access to all businesses.

- No more than one closure is allowed in each direction of travel at the same time.

- Provide at least 1/2 mile between two consecutive shoulder closures or lane closures in the same direction of travel. Connect closures if this distance cannot be provided.

- Consecutive lane closures on the same bound must originate on the same side of the roadway.

- At no time shall traffic be directed or permitted to travel on a milled surface except for cross traffic at intersecting roadways and driveways.

- Close any dedicated lanes (exit, ramp, turn, etc.) prior to the location under construction.

- When a lane is closed, place channelizing devices at cross streets and major drives to form a radius that clearly defines the approaches to the through and turning traffic.

- Perform work and lane closures within the allowable time frames as shown in Table 1 and Table 2, unless otherwise stated by the MDOT Program Manager or designee.

Table 1: M-1 Northbound/Southbound Traffic Restrictions

| Closure Type | Start Time | End Time | Mo | Tu | We | Th | Fr | Sa | Su |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Shoulder Closures | 00:00 | 24:00 | ∞ | ∞ | ∞ | ∞ | ∞ | ∞ | ∞ |
| Single Lane Closures | 00:00 | 24:00 | ∞ | ∞ | ∞ | ∞ | ∞ | ∞ | ∞ |
| Double/Triple Lane Closures | 00:00 | 05:00 | 4 | 0 | 0 | 0 | 0 | 4 | 4 |
|  | 05:00 | 20:00 | 0 | 0 | 0 | 0 | 0 | 4 | 4 |
|  | 20:00 | 24:00 | 0 | 0 | 0 | 0 | 4 | 4 | 4 |
| ∞ = Closure is allowed, and the frequency is not limited during the project timeframe # = The number of times closures can take place during the project timeframe. * Maintain a minimum of one lane of travel in each direction at all times. |  |  |  |  |  |  |  |  |  |

Table 2: M-3 Northbound Traffic Restrictions

| Closure Type | Start Time | End Time | Mo | Tu | We | Th | Fr | Sa | Su |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Shoulder Closures | 00:00 | 24:00 | ∞ | ∞ | ∞ | ∞ | ∞ | ∞ | ∞ |
| Single Lane Closures | 00:00 | 24:00 | ∞ | ∞ | ∞ | ∞ | ∞ | ∞ | ∞ |
| Double Lane Closures | 00:00 | 24:00 | Two Consecutive Weeks |  |  |  |  |  |  |
| ∞ = Closure is allowed, and the frequency is not limited during the project timeframe # = The number of times closures can take place during the project timeframe. |  |  |  |  |  |  |  |  |  |

- Do not work, deliver material, or close lanes during the Holiday Periods as defined by the MDOT Program Manager (Memorial Day, Independence Day, Labor Day, Thanksgiving).

- Do not work, deliver material, or close lanes during any Special Events as defined by Table 3.

Table 3: 2026 Special Events

| Local Event | Start Date and Time | End Date and Time |
| --- | --- | --- |
| Detroit Grand Prix | 3:00 p.m. Monday, May 25th | 6:00 a.m. Wednesday, June 3rd |
| Freedom Festival Fireworks | TBD | TBD |
| Rocket Mortgage Classic | TBD | TBD |
| Woodward Dream Cruise | TBD | TBD |
| Little Caesars Arena | As directed by the Engineer | As directed by the Engineer |
| Special Events and Home | As directed by the Engineer | As directed by the Engineer |
| Ford Field Special Events and Home Games | As directed by the Engineer | As directed by the Engineer |

  - Additional Traffic Control Requirements

- Work must be coordinated with other contractors working in the area per the MDOT Standard Specifications for Construction, Subsection 104.08. Cooperation by the Contractor.

- Access to businesses, residences, hospitals, and fire hydrants in the work zone must be maintained at all times.  Access for emergency vehicles (fire, ambulance, and Police) must be maintained to adjacent homes, businesses, and residences at all times..

- The Contractor must maintain the bus stop or coordinate the work and/or lane closure with the affected bus line.  Contact the appropriate bus line coordinator a minimum of five (5) business days prior to starting work.

- The bus line coordinator for the Detroit Department of Transportation bus line is Ms. Geena Schofield, Transportation Operations Assistant, at 313-833-7973 or geesch@detroitmi.gov.

- The bus line coordinator(s) for the Suburban Mobility and Regional Transportation (SMART) bus line are Michael A. Karninskas, at 248-419-7906 or Mkarninskas@smartbus.org, and Dana Hilthon at 248-419-7905 or dhilthon@smartbus.org.

  - Open to Traffic

Temporary or permanent pavement markings must be in place prior to opening the high friction surface treatment work to traffic. Temporary pavement markings will be Wet Reflective Type NR Paint. All areas must be swept clean of dirt and debris prior to opening to traffic.

| ☐ | I have reviewed Section 3 requirements and agree with no exception. |
| --- | --- |
| ☐ | I have reviewed Section 3 requirements and have noted all exception(s) below. |
| List all exception(s): |  |

- BOND REQUIREMENTS

The Contractor must furnish performance and lien bonds each for not less than 100% of the total contract price.  The bonds must be on forms provided by MDOT.  The bonds must meet the requirements of Michigan law and MDOT and include other items such as the Powers of Attorney and Endorsement as specified by MDOT.  The same surety responsible for writing the performance bond must write the lien bond.  It is the Contractor’s responsibility to ensure that the lien bond conforms with the terms of MCL 570.101 et seq.

| ☐ | I have reviewed Section 4 requirements and agree with no exception. |
| --- | --- |
| ☐ | I have reviewed Section 4 requirements and have noted all exception(s) below. |
| List all exception(s): |  |

- PROJECT PREVAILING WAGE REQUIREMENTS

The Contractor (and its Subcontractors) must pay all mechanics and laborers employed directly on the site of the work, unconditionally and at least once a week, and without subsequent deduction or rebate on any account, the full amounts accrued at time of payment, computed at wage rates not less than those stated in the advertised specifications as prevailing wages based on locality, regardless of any contractual relationship which may be alleged to exist between the Contractor or subcontractor and the laborers and mechanics.

Contractor must post the scale of wages to be paid in a prominent and easily accessible place at the site of the work.  See Attachment A – Prevailing Wage Information and Rates for Oakland County for scale of wages.  The Attachment A rate schedule, along with Prevailing Wage Rates for all counties, may also be found at LEO - Prevailing Wages By County.

Certified payroll must be submitted through the MDOT labor compliance program tracker (LCPTracker) website LCPtracker.  The Contractor must specify a Certified Payroll Approver who will be responsible for entering certified payroll in LCPTracker.

Certified Payroll Approver Contact Information

| Name |  |
| --- | --- |
| Email Address |  |
| Phone Number |  |

| ☐ | I have reviewed Section 5 requirements and agree with no exception. |
| --- | --- |
| ☐ | I have reviewed Section 5 requirements and have noted all exception(s) below. |
| List all exception(s): |  |

- SERVICE REQUIREMENTS

  - Timeframes

- All Contract Activities should be completed by September 30, 2026.

- Once work commences on a street/repair location, Contract Activities must be performed and completed under continuous operations.

- The Contractor will maintain construction activities with downtime accounting only for rain days, regular breaks between workdays, and time needed for curing, unless otherwise approved by the MDOT Program Manager.

- The Contractor must remove all equipment and traffic control devices no later than seven (7) calendar days after work completion.

  - Work Hours

- Perform work and lane closures within the allowable time frames as shown in the above Section 3.4 unless otherwise stated by the MDOT Program Manager.

- Should the Contractor elect to work during nighttime hours, nighttime operations must comply with Section 812.03.H. Lighting for Night Work of the Standard Specifications for Construction.  The cost of night lighting will not be paid for separately and must be included in the cost of the other contract items.

| ☐ | I have reviewed Section 6 requirements and agree with no exception. |
| --- | --- |
| ☐ | I have reviewed Section 6 requirements and have noted all exception(s) below. |
| List all exception(s): |  |

- QUALITY CONTROL

The Contractor must provide personnel and testing equipment necessary to perform required tests for quality control. Quality Control and Quality Assurance for HMA must comply with Special Provision 20SP-501R-06 Superpave Hot Mix Asphalt Percent within Limits (see 20SP-501R-06).  All costs associated with the work are included in the unit prices of the relevant items and will not be paid separately.

| ☐ | I have reviewed Section 7 requirements and agree with no exception. |
| --- | --- |
| ☐ | I have reviewed Section 7 requirements and have noted all exception(s) below. |
| List all exception(s): |  |

- ACCEPTANCE

  - Acceptance, Inspection, and Testing

The State will use the following criteria to determine acceptance of Contract Activities:

•	Visual inspection

•	The Contractor provided an effective quality control plan; and provided personnel and testing equipment necessary to perform the required tests for quality control.

  - Final Acceptance

The MDOT Program Manager or designee will determine final acceptance of the work performed and ensure conformance to the MDOT 2020 Standard Specifications for Construction.

| ☐ | I have reviewed Section 8 requirements and agree with no exception. |
| --- | --- |
| ☐ | I have reviewed Section 8 requirements and have noted all exception(s) below. |
| List all exception(s): |  |

- STAFFING

  - Contractor Program Manager

The Contractor must appoint one individual who will be MDOT’s primary contact, who will be specifically assigned to State of Michigan accounts, and who will respond to State inquiries regarding the Contract Activities (the “Contractor Program Manager”).

The Contractor must notify the Contract Administrator at least 14 calendar days before removing or assigning a new Contractor Program Manager.

Contractor Program Manager Contact Information

| Name |  |
| --- | --- |
| Title |  |
| Office Phone |  |
| Mobile Phone |  |
| Email Address |  |

  - Emergency Contact and 24/7 Telephone Number

The Contractor must specify two emergency contacts who must be available 24 hours a day, 7 days a week to receive emergency work orders or if the Contractor Program Manager cannot be reached.

Primary Emergency Contact Information

| Name |  |
| --- | --- |
| Title |  |
| 24/7 Phone Number |  |

Secondary Emergency Contact Information

| Name |  |
| --- | --- |
| Title |  |
| 24/7 Phone Number |  |

  - Disclosure of Subcontractors

Per MDOT 2020 Standard Specifications for Construction, Section 108.01, if any Contract Activities will be performed by a sub-contractor(s), the sub-contractor(s) must be prequalified by MDOT to perform the classification of the proposed work.  The Contractor must use its own organization to perform work amounting to not less than 35% of the contract amount.

Note:  All listed subcontractors must be registered with LEO as State Project Contractors.  A copy of each subcontractor’s active State Project Registration Confirmation letter must be submitted with bidder’s solicitation response.

If the Contractor intends to utilize subcontractors, the Contractor must disclose the following:

| The legal business name, address, telephone number of the subcontractor(s): |  |
| --- | --- |
| A description of subcontractor’s organization and the services it will provide and information concerning subcontractor’s ability to provide the Contract Activities: |  |
| The relationship of the subcontractor to the Bidder: |  |
| Whether the Bidder has a previous working experience with the subcontractor. If yes, provide the details of that previous relationship: |  |
| A complete description of the Contract Activities that will be performed or provided by the subcontractor: |  |
| Of the total bid, the price of the subcontractor’s work: |  |

| Bidder must provide information based on the work performed by all subcontractors |  |
| --- | --- |
| Total percentage of work that will be performed by subcontractors: |  |

- PROJECT MANAGEMENT

  - Project Control

The Contractor will carry out this project under the direction and control of the MDOT Program Manager. Any questions regarding Contract Activities are to be addressed to the MDOT Program Manager. The MDOT Program Manager for this project is:

Sami Kaffarani

MDOT – Detroit Transportation Service Center

1060 W. Fort St.

Detroit, MI  48226

KaffaraniS@michigan.gov

313-969-7055

  - Project Plan

Within 21 calendar days of Contract execution, the Contractor must submit a project plan to the MDOT Program Manager for final approval.  The plan must include: (a) the Contractor's organizational chart with names and title of personnel assigned to the project; (b) the project breakdown showing sub-projects, tasks, and resources required; and (c) other pertinent information to help guide both project execution and project control.

  - Reporting

The Contractor must submit to the MDOT Program Manager the following written reports:

- Quality Control Plans

- Concrete Mix Design

  - Meetings

- Preconstruction Meeting.  The Contractor may be required to attend a preconstruction meeting with the MDOT Program Manager.  The Program Manager will determine the time and place for the preconstruction meeting. The meeting will be conducted after project award and may be rescheduled if there are delays in the award of the project.

- Preproduction Meeting.  The Contractor must attend a preproduction meeting to go over the concrete mix design and material specifications.  The meeting time/date will be determined after the preconstruction meeting.

- Other Meetings.  The State may request other meetings as it deems appropriate.

| ☐ | I have reviewed Section 10 requirements and agree with no exception. |
| --- | --- |
| ☐ | I have reviewed Section 10 requirements and have noted all exception(s) below. |
| List all exception(s): |  |

- PRICING

Pricing is firm for the entire length of the Contract.

No separate payment will be made for any Item that is not specifically set forth on Schedule B and all costs therefore shall be included in the prices named on Schedule B for the various appurtenant Items of Work.

| ☐ | I have reviewed Section 11 requirements and agree with no exception. |
| --- | --- |
| ☐ | I have reviewed Section 11 requirements and have noted all exception(s) below. |
| List all exception(s): |  |

- ORDER AUTHORIZING DOCUMENT

The appropriate authorizing document for the Contract will be a mutually signed State issued Purchase Order Contract.

| ☐ | I have reviewed Section 12 requirements and agree with no exception. |
| --- | --- |
| ☐ | I have reviewed Section 12 requirements and have noted all exception(s) below. |
| List all exception(s): |  |

- INVOICE AND PAYMENT

  - Invoice Requirements

All invoices submitted to the State must indicate: (a) invoice date; (b) vendor-generated invoice number; (c) purchase order/contract number; (d) description of the Contract Activities (pay item); (e) date of service; (f) quantity; (g) unit price; and (h) total price.

Overtime, holiday pay, and travel expenses will not be paid.

  - Payment Terms

Payment terms are Net 45 Days.

  - Payment Methods

As required by MCL 18.1283, the State will only disburse payments under this Contract through Electronic Funds Transfer (EFT).

The Contractor is responsible for ensuring current banking information is entered in the State vendor website: AdvantageVSS - SIGMA VSS (michigan.gov).

  - Procedure

All invoices must be submitted within 30 days of final work acceptance at the specific location.  All invoices must be submitted via e-mail to MDOT-Metro-DetroitTSC-Invoices@michigan.gov , CC: Sami Kaffarani KaffaraniS@michigan.gov.

| ☐ | I have reviewed Section 13 requirements and agree with no exception. |
| --- | --- |
| ☐ | I have reviewed Section 13 requirements and have noted all exception(s) below. |
| List all exception(s): |  |

- LIQUIDATED DAMAGES

Late or improper completion of the Contract Activities will cause loss and damage to the State and it would be impracticable and extremely difficult to fix the actual damage sustained by the State. Therefore, if Contract Activities are not completed by the date identified in the Statement of Work, the State is entitled to collect liquidated damages in accordance with the Table 108-1 of the 2020 Standard Specifications for Construction for each day Contractor fails to remedy the late or improper completion of the Work.

| Table 108-1: Schedule of Liquidated Damages For Department Oversight |  |  |
| --- | --- | --- |
| Original Contract Amount |  | Amount per Calendar Day |
| From More Than | To and Including |  |
| $0 | $100,000 | $500 |
| $100,000 | $500,000 | $800 |
| $500,000 | $1,000,000 | $1,000 |
| $1,000,000 | $5,000,000 | $1,500 |
| $5,000,000 | $15,000,000 | $2,000 |
| Over $15,000,000 |  | $4,000 |

| ☐ | I have reviewed Section 14 requirements and agree with no exception. |
| --- | --- |
| ☐ | I have reviewed Section 14 requirements and have noted all exception(s) below. |
| List all exception(s): |  |

- ADA COMPLIANCE

The State is required to comply with the Americans with Disabilities Act of 1990 (ADA), including its accessibility standard for websites, applications, content and documents. All Contract Activities created, provided, or made available by Contractor under this Contract in a digital format, including but not limited to, websites, applications, software, mobile applications, text, images, sounds, videos, controls, animations, links, and documents (including files in the following formats: PDF, word processing, presentation, and spreadsheet) must comply with the accessibility standards provided in the Digital Accessibility Standards, located at https://www.michigan.gov/standards.

| ☐ | I have reviewed Section 15 requirements and agree with no exception. |
| --- | --- |
| ☐ | I have reviewed Section 15 requirements and have noted all exception(s) below. |
| List all exception(s): |  |

# Standard Contract terms

This STANDARD CONTRACT (“Contract”) is agreed to between the State of Michigan (the “State”) and the Contractor. This Contract will be effective approximately May 15, 2026 (“Effective Date”), and unless terminated, will expire on October 15, 2026 (the “Term”).

The parties agree as follows:

- Duties of Contractor. Contractor must perform the services and provide the deliverables (the “Contract Activities”) described in a Statement of Work, the initial Statement of Work is attached as Schedule A – Statement of Work.  An obligation to provide delivery of any commodity is considered a service and is a Contract Activity.

Contractor must furnish all labor, equipment, materials, and supplies necessary for the performance of the Contract Activities unless otherwise specified in a Statement of Work.

Contractor must: (a) perform the Contract Activities in accordance with this Contract, including the Statement of Work contained in Schedule A and the 2020 Standard Specifications for Construction; however, in the case of a conflict, Schedule A will control; (b) meet or exceed the performance and operational standards, and specifications of the Contract; (c) provide all Contract Activities in good quality, with no material defects; (d) not interfere with the State’s operations; (e) obtain and maintain all necessary licenses, permits or other authorizations necessary for the performance of the Contract; (f) cooperate with the State, including the State’s quality assurance personnel, and any third party to achieve the objectives of the Contract; (g) return to the State any State-furnished equipment or other resources in the same condition as when provided when no longer required for the Contract; (h) assign to the State any claims resulting from state or federal antitrust violations to the extent that those violations concern materials or services supplied by third parties toward fulfillment of the Contract; (i) comply with all State physical and IT security policies and standards which will be made available upon request; and (j) provide the State priority in performance of the Contract except as mandated by federal disaster response requirements. Any breach under this paragraph is considered a material breach.

Contractor must also be clearly identifiable while on State property by wearing identification issued by the State, and clearly identify themselves whenever making contact with the State.

- Notices. All notices and other communications required or permitted under this Contract must be in writing and will be considered given and received: (a) when verified by written receipt if sent by courier; (b) when actually received if sent by mail without verification of receipt; or (c) when verified by automated receipt or electronic logs if sent by facsimile or email.

| If to State: | If to Contractor: |
| --- | --- |
| Ruth Thole MDOT Contract Services Division 425 W. Ottawa St. Lansing, MI 48933 TholeR@michigan.gov 517-335-4972 |  |

- Contract Administrator. The Contract Administrator, or the individual duly authorized for each party, is the only person authorized to modify any terms of this Contract, and approve and execute any change under this Contract (each a “Contract Administrator”):

| State: | Contractor: |
| --- | --- |
| Ruth Thole MDOT Contract Services Division 425 W. Ottawa St. Lansing, MI 48933 TholeR@michigan.gov 517-335-4972 |  |

- Program Manager. The Program Manager for each party will monitor and coordinate the day-to-day activities of the Contract (each a “Program Manager”):

| State: | Contractor: |
| --- | --- |
| Sami Kaffarani MDOT – Detroit Transportation Service Center 1060 W. Fort St. Detroit, MI 48226 KaffaraniS@michigan.gov 313-969-7055 |  |

- Performance Guarantee. Contractor must at all times have financial resources sufficient, in the opinion of the State, to ensure performance of the Contract and must provide proof upon request. The State may require a performance bond (as specified in a Statement of Work) if, in the opinion of the State, it will ensure performance of the Contract.

- Insurance Requirements. Contractor, at its sole expense, must maintain the insurance coverage identified below. All required insurance must: (a) protect the State from claims that may arise out of, are alleged to arise out of, or otherwise result from Contractor's or a subcontractor's performance; (b) be primary and non-contributing to any comparable liability insurance (including self-insurance) carried by the State; and (c) be provided by a company with an A.M. Best rating of "A-" or better, and a financial size of VII or better.

TABLE 6.1

| Required Limits | Additional Requirements |
| --- | --- |
| Commercial General Liability Insurance |  |
| Minimum Limits: $1,000,000 Each Occurrence $1,000,000 Personal & Advertising Injury $2,000,000 Products/Completed Operations $2,000,000 General Aggregate | Contractor must have their policy endorsed to add “the State of Michigan, its departments, divisions, agencies, offices, commissions, officers, employees, and agents” as additional insureds using endorsement CG 20 10 11 85, or both CG 20 10 12 19 and CG 20 37 12 19. |
| Umbrella or Excess Liability Insurance |  |
| Minimum Limits: $5,000,000 General Aggregate | Contractor must have their policy follow form. |
| Automobile Liability Insurance |  |
| Minimum Limits: $1,000,000 Per Accident | Contractor must have their policy: (1) endorsed to add “the State of Michigan, its departments, divisions, agencies, offices, commissions, officers, employees, and agents” as additional insureds; and (2) include Hired and Non-Owned Automobile coverage. |
| Workers' Compensation Insurance |  |
| Minimum Limits: Coverage according to applicable laws governing work activities. | Waiver of subrogation, except where waiver is prohibited by law. |
| Employers Liability Insurance |  |
| Minimum Limits: $500,000 Each Accident $500,000 Each Employee by Disease $500,000 Aggregate Disease |  |

If any of the required policies provide claims-made coverage, the Contractor must: (a) provide coverage with a retroactive date before the Effective Date of the Contract or the beginning of Contract Activities; (b) maintain coverage and provide evidence of coverage for at least 3 years after completion of the Contract Activities; and (c) if coverage is cancelled or not renewed, and not replaced with another claims-made policy form with a retroactive date prior to the Contract Effective Date, Contractor must purchase extended reporting coverage for a minimum of 3 years after completion of work.

Contractor must: (a) provide insurance certificates to the Contract Administrator, containing the agreement or delivery order number, at Contract formation and within 20 calendar days of the expiration date of the applicable policies; (b) require that subcontractors maintain the required insurance contained in this Section; (c) notify the Contract Administrator within 5 business days if any insurance is cancelled; and (d) waive all rights against the State for damages covered by insurance. Failure to maintain the required insurance does not limit this waiver.

This Section is not intended to and is not to be construed in any manner as waiving, restricting or limiting the liability of either party for any obligations under this Contract (including any provisions hereof requiring Contractor to indemnify, defend and hold harmless the State).

- Reserved.

- Reserved.

- Relationship of the Parties. The relationship between the parties is that of independent contractors. Contractor, its employees, and agents will not be considered employees of the State. No partnership or joint venture relationship is created by virtue of this Contract. Contractor, and not the State, is responsible for the payment of wages, benefits and taxes of Contractor’s employees and any subcontractors. Prior performance does not modify Contractor’s status as an independent contractor. Neither party has authority to contract for nor bind the other party in any manner whatsoever.

Intellectual Property Rights. If a Statement of Work requires Contractor to create any intellectual property, Contractor hereby acknowledges that the State is and will be the sole and exclusive owner of all right, title, and interest in the Contract Activities and all associated intellectual property rights, if any. Such Contract Activities are works made for hire as defined in Section 101 of the Copyright Act of 1976. To the extent any Contract Activities and related intellectual property do not qualify as works made for hire under the Copyright Act, Contractor will, and hereby does, immediately on its creation, assign, transfer and otherwise convey to the State, irrevocably and in perpetuity, throughout the universe, all right, title and interest in and to the Contract Activities, including all intellectual property rights therein.

- Subcontracting. Contractor may subcontract work in accordance with Subsection 108.01 of the 2020 Standard Specifications for Construction.

- Staffing. The State’s Contract Administrator may require Contractor to remove or reassign personnel providing services by providing a notice to Contractor.

- Background Checks. Pursuant to Michigan law, all agencies subject to IRS Pub. 1075 are required to ask the Michigan State Police to perform fingerprint background checks on all employees, including Contractor and Subcontractor employees, who may have access to any database of information maintained by the federal government that contains confidential or personal information, including, but not limited to, federal tax information. Further, pursuant to Michigan law, any agency described above is prohibited from providing Contractors or Subcontractors with the result of such background check. For more information, please see Michigan Public Act 427 of 2018. Upon request, or as may be specified in a Statement of Work, Contractor must perform background checks on all employees and subcontractors and its employees prior to their assignment. The scope is at the discretion of the State and documentation must be provided as requested. Contractor is responsible for all costs associated with the requested background checks. The State, in its sole discretion, may also perform background checks.

- Assignment. Contractor may not assign this Contract to any other party without the prior approval of the State. Upon notice to Contractor, the State, in its sole discretion, may assign in whole or in part, its rights or responsibilities under this Contract to any other party. If the State determines that a novation of the Contract to a third party is necessary, Contractor will agree to the novation and provide all necessary documentation and signatures.

- Change of Control. Contractor will notify the State, within 30 days of any public announcement or otherwise once legally permitted to do so, of a change in Contractor’s organizational structure or ownership. For purposes of this Contract, a change in control means any of the following: (a) a sale of more than 50% of Contractor’s stock; (b) a sale of substantially all of Contractor’s assets; (c) a change in a majority of Contractor’s board members; (d) consummation of a merger or consolidation of Contractor with any other entity; (e) a change in ownership through a transaction or series of transactions; (f) or the board (or the stockholders) approves a plan of complete liquidation. A change of control does not include any consolidation or merger effected exclusively to change the domicile of Contractor, or any transaction or series of transactions principally for bona fide equity financing purposes.

In the event of a change of control, Contractor must require the successor to assume this Contract and all of its obligations under this Contract.

- Ordering. Contractor is not authorized to begin performance until receipt of authorization as identified in a Statement of Work.

- Acceptance. Contract Activities are subject to inspection and testing by the State within 30 calendar days of the State’s receipt of them (“State Review Period”), unless otherwise provided in a Statement of Work.  The State’s approvals, reviews, and inspections do not relieve the Contractor of its contractual obligations. The Contractor understands that any approvals, reviews, or inspections are undertaken for the sole use and information of the State and will not serve as a warranty as to the propriety of the Contractor’s performance.

If the Contract Activities are not fully accepted by the State, the State will notify Contractor by the end of the State Review Period that either: (a) the Contract Activities are accepted but noted deficiencies must be corrected; or (b) the Contract Activities are rejected. If the State finds material deficiencies, it may: (i) reject the Contract Activities without performing any further inspections; (ii) demand performance at no additional cost; or (iii) terminate this Contract in accordance with Section 24, Termination for Cause.

Within 10 business days from the date of Contractor’s receipt of notification of acceptance with deficiencies or rejection of any Contract Activities, Contractor must cure, at no additional cost, the deficiency and deliver unequivocally acceptable Contract Activities to the State. If acceptance with deficiencies or rejection of the Contract Activities impacts the content or delivery of other non-completed Contract Activities, the parties’ respective Program Managers must determine an agreed to number of days for re-submission that minimizes the overall impact to the Contract. However, nothing herein affects, alters, or relieves Contractor of its obligations to correct deficiencies in accordance with the time response standards set forth in this Contract.

If Contractor is unable or refuses to correct the deficiency within the time response standards set forth in this Contract, the State may cancel the order in whole or in part. The State, or a third party identified by the State, may perform the Contract Activities and recover the difference between the cost to cure and the Contract price.

- Reserved.

- Reserved.

- Warranty Period. The warranty period, if applicable, for Contract Activities is a fixed period commencing on the date specified in a Statement of Work. If the Contract Activities do not function as warranted during the warranty period, the State may return such non-conforming Contract Activities to the Contractor for a full refund.

- Invoices and Payment. Invoices must conform to the requirements communicated from time-to-time by the State. All undisputed amounts are payable within 45 days of the State’s receipt. Contractor may only charge for Contract Activities provided as specified in a Statement of Work. Invoices must include an itemized statement of all charges. The State is exempt from federal excise tax, state and local sales taxes, and use taxes if the Contract Activities purchased under this Contract are for the State’s exclusive use. Contractor will not include the collection of taxes for which the State is exempt in any invoices or payments related to this Contract. The State is not responsible for taxes imposed or assessed on Contractor.

The State has the right to withhold payment of any disputed amounts until the parties agree as to the validity of the disputed amount. The State will notify Contractor of any dispute within a reasonable time. Payment by the State will not constitute a waiver of any rights as to Contractor’s continuing obligations, including claims for deficiencies or substandard Contract Activities. Contractor’s acceptance of final payment by the State constitutes a waiver of all claims by Contractor against the State for payment under this Contract, other than those claims previously filed in writing on a timely basis and still disputed.

The State will only disburse payments under this Contract through Electronic Funds Transfer (EFT). Contractor must register with the State at http://www.michigan.gov/SIGMAVSS to receive electronic fund transfer payments. If Contractor does not register, the State is not liable for failure to provide payment. Without prejudice to any other right or remedy it may have, the State reserves the right to set off at any time any amount then due and owing to it by Contractor against any amount payable by the State to Contractor under this Contract.

Excluding federal government charges and terms, Contractor warrants and agrees that each of the fees, economic or product terms or warranties granted pursuant to this Contract are comparable to or better than the equivalent fees, economic or product term or warranty being offered to any commercial or government customer (including any public educational institution within the State of Michigan) of Contractor.  If Contractor enters into any arrangements with another customer of Contractor to provide the products or services, available under this Contract, under more favorable prices, as the prices may be indicated on Contractor’s current U.S. and International price list or comparable document, then this Contract will be deemed amended as of the date of such other arrangements to incorporate those more favorable prices, and Contractor will immediately notify the State of such fee and formally memorialize the new pricing in a change notice.

- Liquidated Damages. Liquidated damages will be assessed as described in a Statement of Work. The parties understand and agree that any liquidated damages (which includes but is not limited to applicable credits) set forth in this Contract are reasonable estimates of the State’s damages in accordance with applicable law. The parties acknowledge and agree that Contractor could incur liquidated damages for more than 1 event. The assessment of liquidated damages will not constitute a waiver or release of any other remedy the State may have under this Contract for Contractor’s breach of this Contract, including without limitation, the State’s right to terminate this Contract for cause under Section 24 and the State will be entitled in its discretion to recover actual damages caused by Contractor’s failure to perform its obligations under this Contract.  However, the State will reduce such actual damages by the amounts of liquidated damages received for the same events causing the actual damages.  Amounts due the State as liquidated damages may be set off against any fees payable to Contractor under this Contract, or the State may bill Contractor as a separate item and Contractor will promptly make payments on such bills.

- Stop Work Order. The State may suspend any or all activities under the Contract at any time. The State will provide Contractor a written stop work order detailing the suspension. Contractor must comply with the stop work order upon receipt. Within 90 calendar days, or any longer period agreed to by Contractor, the State will either: (a) issue a notice authorizing Contractor to resume work, or (b) terminate the Contract or delivery order. The State will not pay for Contract Activities, Contractor’s lost profits, or any additional compensation during a stop work period.

- Termination for Cause. (a) The State may terminate this Contract for cause, in whole or in part, if Contractor, as determined by the State: (i) endangers the value, integrity, or security of any facility, data, or personnel; (ii) becomes insolvent, petitions for bankruptcy court proceedings, or has an involuntary bankruptcy proceeding filed against it by any creditor; (iii) engages in any conduct that may expose the State to liability; (iv) breaches any of its material duties or obligations under this Contract; or (v) fails to cure a breach within the time stated by the State in a notice of breach, if in its sole discretion the State has chosen to provide a time to cure. Any reference to specific breaches being material breaches within this Contract will not be construed to mean that other breaches are not material.

(b) If the State terminates this Contract under this Section, the State will issue a termination notice specifying whether Contractor must: (i) cease performance immediately. Contractor must submit all invoices for Contract Activities accepted by the State within 30 days of the date of termination. Failure to submit an invoice within that timeframe will constitute a waiver by Contractor for any amounts due to Contactor for Contract Activities accepted by the State under this Contract or (ii) continue to perform for a specified period. If it is later determined that Contractor was not in breach of the Contract, the termination will be deemed to have been a Termination for Convenience, effective as of the same date, and the rights and obligations of the parties will be limited to those provided in Section 25, Termination for Convenience.

The State will only pay for amounts due to Contractor for Contract Activities accepted by the State on or before the date of termination, subject to the State’s right to set off any amounts owed by the Contractor for the State’s reasonable costs in terminating this Contract. Contractor must promptly reimburse to the State any fees prepaid by the State prorated to the date of such termination, including any prepaid fees. The Contractor must pay all reasonable costs incurred by the State in terminating this Contract for cause, including administrative costs, attorneys’ fees, court costs, transition costs, and any costs the State incurs to procure the Contract Activities from other sources.

Termination for Convenience. The State may immediately terminate this Contract in whole or in part without penalty and for any reason or no reason, including but not limited to, appropriation or budget shortfalls. The termination notice will specify whether Contractor must: (a) cease performance of the Contract Activities immediately. Contractor must submit all invoices for Contract Activities accepted by the State within 30 days of the date of termination. Failure to submit an invoice within that timeframe will constitute a waiver by Contractor for any amounts due Contractor for Contract Activities accepted by the State under this Contract, or (b) continue to perform the Contract Activities in accordance with Section 26, Transition Responsibilities. If the State terminates this Contract for convenience, the State will pay all reasonable costs, as determined by the State, for State approved Transition Responsibilities to the extent the funds are available.

- Transition Responsibilities. Upon termination or expiration of this Contract for any reason, Contractor must, for a period of time specified by the State (not to exceed 90 calendar days), provide all reasonable transition assistance requested by the State, to allow for the expired or terminated portion of the Contract Activities to continue without interruption or adverse effect, and to facilitate the orderly transfer of such Contract Activities to the State or its designees. Such transition assistance may include, but is not limited to: (a) continuing to perform the Contract Activities at the established Contract rates; (b) taking all reasonable and necessary measures to transition performance of the work, including all applicable Contract Activities, training, equipment, software, leases, reports and other documentation, to the State or the State’s designee;  (c) transferring title in and delivering to the State, at the State’s discretion, all completed or partially completed deliverables prepared under this Contract as of the Contract termination date; and (d) preparing an accurate accounting from which the State and Contractor may reconcile all outstanding accounts (collectively, “Transition Responsibilities”). This Contract will automatically be extended through the end of the transition period.

- Return of State Property. Upon termination or expiration of this Contract for any reason, Contractor must take all necessary and appropriate steps, or such other action as the State may direct, to preserve, maintain, protect, or return to the State all materials, data, property, and confidential information provided directly or indirectly to the Contractor by any entity, agent, vendor, or employee of the State.

Indemnification. Contractor must defend, indemnify and hold the State, its departments, divisions, agencies, offices, commissions, officers, and employees harmless, without limitation, from and against any and all actions, claims, losses, liabilities, damages, costs, attorney fees, and expenses (including those required to establish the right to indemnification) arising out of the performance of the work until the Contractor achieves satisfactory final inspection in accordance with Subsection 109.07.C.1 of the Standard Specifications for Construction.  The Contractor will not be responsible for claims that result from the sole negligence or willful acts or omissions of said indemnitees.

The State will notify Contractor in writing if indemnification is sought; however, failure to do so will not relieve Contractor of this obligation. Contractor must, to the satisfaction of the State, demonstrate its financial ability to carry out these obligations.

The State is entitled to: (i) regular updates on proceeding status; (ii) participate in the defense of the proceeding; (iii) employ its own counsel; and to (iv) retain control of the defense, at its own cost and expense, if the State deems necessary. Contractor will not, without the State’s prior written consent (not to be unreasonably withheld), settle, compromise, or consent to the entry of any judgment in or otherwise seek to terminate any claim, action, or proceeding.

Any litigation activity on behalf of the State, or any of its subdivisions under this Section, must be coordinated with the Department of Attorney General. An attorney designated to represent the State may not do so until approved by the Michigan Attorney General and appointed as a Special Assistant Attorney General.

The State is constitutionally prohibited from indemnifying Contractor or any third parties.

- Infringement Remedies. If, in either party’s opinion, any piece of equipment, software, commodity, or service supplied by Contractor or its subcontractors, or its operation, use or reproduction, is likely to become the subject of a copyright, patent, trademark, or trade secret infringement claim, Contractor must, at its expense: (a) procure for the State the right to continue using the equipment, software, commodity, or service, or if this option is not reasonably available to Contractor, (b) replace or modify the same so that it becomes non-infringing; or (c) accept its return by the State with appropriate credits to the State against Contractor’s charges and reimburse the State for any losses or costs incurred as a consequence of the State ceasing its use and returning it.

- Limitation of Liability and Disclaimer of Damages. IN NO EVENT WILL THE STATE’S AGGREGATE LIABILITY TO CONTRACTOR UNDER THIS CONTRACT, REGARDLESS OF THE FORM OF ACTION, WHETHER IN CONTRACT, TORT, NEGLIGENCE, STRICT LIABILITY OR BY STATUTE OR OTHERWISE, FOR ANY CLAIM RELATED TO OR ARISING UNDER THIS CONTRACT, EXCEED THE CONTRACT PRICE. The State is not liable for consequential, incidental, indirect, or special damages, regardless of the nature of the action.

- Disclosure of Litigation, or Other Proceeding. Contractor must notify the State within 14 calendar days of receiving notice of any litigation, investigation, arbitration, or other proceeding (collectively, “Proceeding”) involving Contractor, a subcontractor, or an officer or director of Contractor or subcontractor, that arises during the term of the Contract, including: (a) a criminal Proceeding; (b) a parole or probation Proceeding; (c) a Proceeding under the Sarbanes-Oxley Act; (d) a civil Proceeding involving: (1) a claim that might reasonably be expected to adversely affect Contractor’s viability or financial stability; or (2) a governmental or public entity’s claim or written allegation of fraud; or (3) any complaint filed in a legal or administrative proceeding alleging the Contractor or its subcontractors discriminated against its employees, subcontractors, vendors, or suppliers during the term of this Contract; or (e) a Proceeding involving any license that Contractor is required to possess in order to perform under this Contract.

Reserved.

Reserved.

- Non-Disclosure of Confidential Information. The parties acknowledge that each party may be exposed to or acquire communication or data of the other party that is confidential, privileged communication not intended to be disclosed to third parties.

  - Meaning of Confidential Information. For the purposes of this Contract, the term “Confidential Information” means all information and documentation of a party that: (a) has been marked “confidential” or with words of similar meaning, at the time of disclosure by such party; (b) if disclosed orally or not marked “confidential” or with words of similar meaning, was subsequently summarized in writing by the disclosing party and marked “confidential” or with words of similar meaning; or, (c) should reasonably be recognized as confidential information of the disclosing party. The term “Confidential Information” does not include any information or documentation that was or is: (a) subject to disclosure under the Michigan Freedom of Information Act (FOIA); (b) already in the possession of the receiving party without an obligation of confidentiality; (c) developed independently by the receiving party, as demonstrated by the receiving party, without violating the disclosing party’s proprietary rights; (d) obtained from a source other than the disclosing party without an obligation of confidentiality; or, (e) publicly available when received, or thereafter became publicly available (other than through any unauthorized disclosure by, through, or on behalf of, the receiving party). For purposes of this Contract, in all cases and for all matters, State Data is deemed to be Confidential Information.

  - Obligation of Confidentiality. The parties agree to hold all Confidential Information in strict confidence and not to copy, reproduce, sell, transfer, or otherwise dispose of, give or disclose such Confidential Information to third parties other than employees, agents, or subcontractors of a party who have a need to know in connection with this Contract or to use such Confidential Information for any purposes whatsoever other than the performance of this Contract. The parties agree to advise and require their respective employees, agents, and subcontractors of their obligations to keep all Confidential Information confidential. Disclosure to a subcontractor is permissible where: (a) use of a subcontractor is authorized under this Contract; (b) the disclosure is necessary or otherwise naturally occurs in connection with work that is within the subcontractor's responsibilities; and (c) Contractor obligates the subcontractor in a written contract to maintain the State's Confidential Information in confidence. At the State's request, any employee of Contractor or any subcontractor may be required to execute a separate agreement to be bound by the provisions of this Section.

  - Cooperation to Prevent Disclosure of Confidential Information. Each party must use its best efforts to assist the other party in identifying and preventing any unauthorized use or disclosure of any Confidential Information. Without limiting the foregoing, each party must advise the other party immediately in the event either party learns or has reason to believe that any person who has had access to Confidential Information has violated or intends to violate the terms of this Contract and each party will cooperate with the other party in seeking injunctive or other equitable relief against any such person.

  - Remedies for Breach of Obligation of Confidentiality. Each party acknowledges that breach of its obligation of confidentiality may give rise to irreparable injury to the other party, which damage may be inadequately compensable in the form of monetary damages. Accordingly, a party may seek and obtain injunctive relief against the breach or threatened breach of the foregoing undertakings, in addition to any other legal remedies which may be available, to include, in the case of the State, at the sole election of the State, the immediate termination, without liability to the State, of this Contract or any Statement of Work corresponding to the breach or threatened breach.

  - Surrender of Confidential Information upon Termination. Upon termination of this Contract or a Statement of Work, in whole or in part, each party must, within 5 calendar days from the date of termination, return to the other party any and all Confidential Information received from the other party, or created or received by a party on behalf of the other party, which are in such party’s possession, custody, or control; provided, however, that Contractor must return State Data to the State following the timeframe and procedure described further in this Contract. Should Contractor or the State determine that the return of any Confidential Information is not feasible, such party must destroy the Confidential Information and must certify the same in writing within 5 calendar days from the date of termination to the other party. However, the State’s legal ability to destroy Contractor data may be restricted by its retention and disposal schedule, in which case Contractor’s Confidential Information will be destroyed after the retention period expires.

Reserved.

- Reserved.

- Reserved.

- Records Maintenance, Inspection, Examination, and Audit. The State or its designee may audit Contractor to verify compliance with this Contract. Contractor must retain and provide to the State or its designee and the auditor general upon request, all records related to the Contract through the term of the Contract and for 4 years after the latter of termination, expiration, or final payment under this Contract or any extension (“Audit Period”). If an audit, litigation, or other action involving the records is initiated before the end of the Audit Period, Contractor must retain the records until all issues are resolved.

Within 10 calendar days of providing notice, the State and its authorized representatives or designees have the right to enter and inspect Contractor's premises or any other places where Contract Activities are being performed, and examine, copy, and audit all records related to this Contract. Contractor must cooperate and provide reasonable assistance. If financial errors are revealed, the amount in error must be reflected as a credit or debit on subsequent invoices until the amount is paid or refunded. Any remaining balance at the end of the Contract must be paid or refunded within 45 calendar days.

This Section applies to Contractor, any parent, affiliate, or subsidiary organization of Contractor, and any subcontractor that performs Contract Activities in connection with this Contract.

- Representations and Warranties. Contractor represents and warrants: (a) Contractor is the owner or licensee of any Contract Activities that it licenses, sells, or develops and Contractor has the rights necessary to convey title, ownership rights, or licensed use; (b) all Contract Activities are delivered free from any security interest, lien, or encumbrance and will continue in that respect; (c) the Contract Activities will not infringe the patent, trademark, copyright, trade secret, or other proprietary rights of any third party; (d) Contractor must assign or otherwise transfer to the State or its designee any manufacturer's warranty for the Contract Activities; (e) the Contract Activities are merchantable and fit for the specific purposes identified in the Contract; (f) the Contract signatory has the authority to enter into this Contract; (g) all information furnished by Contractor in connection with the Contract fairly and accurately represents Contractor's business, properties, finances, and operations as of the dates covered by the information, and Contractor will inform the State of any material adverse changes;(h) all information furnished and representations made in connection with the award of this Contract is true, accurate, and complete, and contains no false statements or omits any fact that would make the information misleading; and that (i) Contractor is neither currently engaged in nor will engage in the boycott of a person based in or doing business with a strategic partner as described in 22 USC 8601 to 8606. A breach of this Section is considered a material breach of this Contract, which entitles the State to terminate this Contract under Section 24, Termination for Cause.

- Conflicts and Ethics. Contractor will uphold high ethical standards and is prohibited from: (a) holding or acquiring an interest that would conflict with this Contract; (b) doing anything that creates an appearance of impropriety with respect to the award or performance of the Contract; (c) attempting to influence or appearing to influence any State employee by the direct or indirect offer of anything of value; or (d) paying or agreeing to pay any person, other than employees and consultants working for Contractor, any consideration contingent upon the award of the Contract. Contractor must immediately notify the State of any violation or potential violation of these standards. This Section applies to Contractor, any parent, affiliate, or subsidiary organization of Contractor, and any subcontractor that performs Contract Activities in connection with this Contract.

- Compliance with Laws. Contractor must comply with all federal, state and local laws, rules and regulations.

- Prevailing Wage Act Statutory Provision. Contractor must comply with prevailing wage requirements, to the extent applicable to this Contract. As required by MCL 408.1112, if the Michigan Prevailing Wage Act, MCL 408.1101 et seq. applies to this Contract, construction mechanics (as defined in MCL 408.1101 (b)) are intended beneficiaries of the contractual prevailing wage, fringe benefit, and nondiscrimination nonretaliation requirements of the Contract. Any construction mechanic aggrieved by the failure of a Contractor or subcontractor to pay prevailing wages or benefits as specified in this Contract, or by a violation of MCL 408.1107, in addition to any other remedies provided in Public Act 10 of 2023 or by law, may bring an action in a court of competent jurisdiction against the Contractor or subcontractor for damages or injunctive relief and may be awarded reinstatement or other appropriate relief, and all damages sustained, together with actual costs and attorney fees at trial and on appeal. If the Michigan Prevailing Wage Act, MCL 408.1101 et seq. applies to this Contract, the rates of wages and fringe benefits to be paid to each class of construction mechanic (as defined in MCL 408.1101 (b)) by Contractor and subcontractors must not be less than the wage and fringe benefit rates prevailing in the locality in which the work is performed.

- Reserved.

- Nondiscrimination. Under the Elliott-Larsen Civil Rights Act, 1976 PA 453, MCL 37.2101, et seq., the Persons with Disabilities Civil Rights Act, 1976 PA 220, MCL 37.1101, et seq., and Executive Directive 2019-09, Contractor and its subcontractors agree not to discriminate against an employee or applicant for employment with respect to hire, tenure, terms, conditions, or privileges of employment, or a matter directly or indirectly related to employment, because of race, color, religion, national origin, age, sex, sexual orientation, gender identity or expression, height, weight, marital status, partisan considerations, any mental or physical disability, or genetic information that is unrelated to the person’s ability to perform the duties of a particular job or position. Breach of this Section is a material breach of this Contract.

- Unfair Labor Practice. Under MCL 423.324, the State may void this Contract if the name of the Contractor, or the name of a subcontractor, manufacturer, or supplier of the Contractor, subsequently appears on the Unfair Labor Practice register compiled under MCL 423.322.

- Governing Law. This Contract is governed, construed, and enforced in accordance with Michigan law, excluding choice-of-law principles. Contractor waives any objections, such as lack of personal jurisdiction or forum non conveniens. Contractor must appoint an agent in Michigan to receive service of process.

- Non-Exclusivity. Nothing contained in this Contract is intended nor is to be construed as creating any requirements contract with Contractor, nor does it provide Contractor with a right of first refusal for any future work. This Contract does not restrict the State or its agencies from acquiring similar, equal, or like Contract Activities from other sources.

- Force Majeure. Neither party will be in breach of this Contract because of any failure arising from any disaster or acts of god that are beyond their control and without their fault or negligence. Each party will use commercially reasonable efforts to resume performance. Contractor will not be relieved of a breach or delay caused by its subcontractors. If immediate performance is necessary to ensure public health and safety, the State may immediately contract with a third party.

- Dispute Resolution. Any disputes under this Contract must follow the claims process detailed in Subsection 104.10 of the 2020 Standard Specifications for Construction.

- Media Releases. News releases (including promotional literature and commercial advertisements) pertaining to the Contract or project to which it relates must not be made without the prior written approval of the State, and then only in accordance with the explicit written instructions of the State.

- Schedules. All Schedules, Exhibits and Attachments that are referenced herein and attached hereto are hereby incorporated by reference. The following Schedules are attached hereto and incorporated herein:

| Document Title | Document Description |
| --- | --- |
| Schedule A | Statement of Work |
| Schedule B | Pricing |

The following Exhibits and Attachments are incorporated into the Contract by reference:

| Document Title | Document Description |
| --- | --- |
| Exhibit 1A | Woodward Ave M-1 Plans |
| Exhibit 1B | Gratiot Ave M-3 Maps & Plans |
| Exhibit 2 | Brick Paver Transport & Storage |
| Exhibit 3 | HMA Mill and Fill Sample |
| Attachment 1 | Prevailing Wage Rates for Oakland County |

- Entire Agreement and Order of Precedence. This Contract, which includes Statement of Work, and schedules and exhibits, is the entire agreement of the parties related to the Contract Activities. This Contract supersedes and replaces all previous understandings and agreements between the parties for the Contract Activities. If there is a conflict between documents, the order of precedence is: (a) first, this Contract, excluding its schedules, exhibits, and Statement of Work; (b) second, Statement of Work as of the Effective Date; (c) third, schedules expressly incorporated into this Contract as of the Effective Date and (d) the 2020 Standard Specifications for Construction. NO TERMS ON CONTRACTOR’S INVOICES, ORDERING DOCUMENTS, WEBSITE, BROWSE-WRAP, SHRINK-WRAP, CLICK-WRAP, CLICK-THROUGH OR OTHER NON-NEGOTIATED TERMS AND CONDITIONS PROVIDED WITH ANY OF THE CONTRACT ACTIVITIES, OR DOCUMENTATION HEREUNDER, EVEN IF ATTACHED TO THE STATE’S DELIVERY OR PURCHASE ORDER, WILL CONSTITUTE A PART OR AMENDMENT OF THIS CONTRACT OR IS BINDING ON THE STATE OR ANY AUTHORIZED USER FOR ANY PURPOSE. ALL SUCH OTHER TERMS AND CONDITIONS HAVE NO FORCE AND EFFECT AND ARE DEEMED REJECTED BY THE STATE AND THE AUTHORIZED USER, EVEN IF ACCESS TO OR USE OF THE CONTRACT ACTIVITIES REQUIRES AFFIRMATIVE ACCEPTANCE OF SUCH TERMS AND CONDITIONS.

- Severability. If any part of this Contract is held invalid or unenforceable, by any court of competent jurisdiction, that part will be deemed deleted from this Contract and the severed part will be replaced by agreed upon language that achieves the same or similar objectives. The remaining Contract will continue in full force and effect.

- Waiver. Failure to enforce any provision of this Contract will not constitute a waiver.

- Survival.  Any right, obligation or condition that, by its express terms or nature and context is intended to survive, will survive the termination or expiration of this Contract; such rights, obligations, or conditions include, but are not limited to, those related to transition responsibilities; indemnification; disclaimer of damages and limitations of liability; State Data; non-disclosure of Confidential Information; representations and warranties; insurance and bankruptcy.

- Contract Modification. This Contract may not be amended except by signed agreement between the parties (a “Contract Change Notice”). Notwithstanding the foregoing, no subsequent Statement of Work or Contract Change Notice executed after the Effective Date will be construed to amend this Contract unless it specifically states its intent to do so and cites the section or sections amended.